## README
Mine Permitting Data Template (Prototype) — How to use
• One record per row per sheet. Do not merge cells. Use IDs to link between sheets. • Dates must be ISO format YYYY-MM-DD. If only month known, use first day (e.g., 2020-05-01) and set Precision to 'month'. • Use the dropdowns for enums. If a value is missing, add it to the Enums sheet. • Multi-value fields should be entered as separate rows in join sheets (e.g., NEPA_Action_Agencies, Case_Links). • Every row should include at least one Source ID pointing to the Sources sheet. • Key relationships: - Projects link to Mines via mine_id. - NEPA_Actions link to Projects via project_id. - NEPA_Action_Agencies link a NEPA action to agencies with a role. - Events, Phases, Delays can link to NEPA actions and/or Permits. - Legal_Cases link to Projects; Case_Links join cases to NEPA actions or Permits.

## Mines
mine_id | name | operator | commodity_primary | commodity_secondary | state | county | lat | lon | land_status_mix | mine_type | tailings_type | description | notes | source_id_primary | created_at | updated_at
morenci_mine | Morenci Mine | Freeport-McMoRan | Copper | Molybdenum | AZ | Greenlee | 33.07 | -109.35 | Primarily private, with some unpatented claims on federal land (BLM) | open-pit | upstream
carlota_mine | Carlota Mine | KGHM | Copper | Silver | AZ | Gila | 33.84 | -110.98 | Federal (BLM, unpatented claims) | open-pit | none_na
bagdad_mine | Bagdad Mine | Freeport-McMoRan | Copper | Molybdenum | AZ | Yavapai | 34.59 | -113.17 |  | open-pit | centerline
ray_mine | Ray Mine | ASARCO | Copper | Gold | AZ | Pinal | 33.14 | -110.98 |  | open-pit | centerline
florence_mine | Florence Mine | Taseko Mines | Copper |  | AZ | Gila | 33 | -110 |  | in-situ | none_na
rosemont_mine | Rosemont Mine | Hudbay Minerals | Copper | Molybdenum | AZ | Pima | 31.85 | -110.75 |  | open-pit | filtered_dry_stack
pinto_valley_mine | Pinto Valley Mine | Capstone Copper | Copper | Molybdenum | AZ | Gila | 33.41 | -110.96 |  | open-pit | upstream
copper_world_mine | Copper World Mine | Hudbay Minerals | Copper | Molybdenum | AZ | Pima | 31.85 | -110.75 |  | open-pit | centerline
northmet_mine | NorthMet Mine | NewRange | Copper |  | MN | St. Louis | 47.62 | -91.94 | Mix of USFS and private | open-pit | conventional
twin_metals_mine | Twin Metals Mine | Twin metals | Copper |  | MN | Lake
pebble_mine | Pebble Mine | Northern Dynasty Minerals | Copper | Gold | AK | Bristol Bay | 59.89 | -155.28
robinson_mine | Robinson Mine | KGHM | Copper |  | NV | Ely
greater_phoenix_mine | Greater Phoenix Mine | Newmont | Copper | Gold | NV
copper_flat_mine | Copper Flat Mine | New Mexico Copper Corporation | Copper |  | NM
montanore_mine | Montanore Mine | Montanore Mining Company | Copper |  | MN
rock_creek_mine | Rock Creek Mine | Hecla Mining Company | Copper | Silver | MN

## Enums
ListName | Value
EventTypes | NOI_Published
EventTypes | Scoping_Start
EventTypes | Scoping_End
EventTypes | DEIS_Published
EventTypes | DEIS_Comment_Open
EventTypes | DEIS_Comment_Close
EventTypes | FEIS_Published
EventTypes | FEIS_Wait_Period_End
EventTypes | ROD_Signed
EventTypes | SEIS_Published
EventTypes | Supplemental_DEIS_Published
EventTypes | Permit_Application_Submitted
EventTypes | Permit_Complete
EventTypes | Permit_Issued
EventTypes | Permit_Denied
EventTypes | Complaint_Filed
EventTypes | Prelim_Injunction_Issued
EventTypes | PI_Lifted
EventTypes | Decision_Issued
PermitTypes | 404_Individual
PermitTypes | 404_Nationwide
PermitTypes | 401_Cert
PermitTypes | AZPDES
PermitTypes | NPDES
PermitTypes | Air_TitleV
PermitTypes | Air_Minor
PermitTypes | APP_UIC
PermitTypes | APP_Aquifer_Protection
PermitTypes | ROW
PermitTypes | Land_Exchange
DelayCategories | Process
DelayCategories | Execution
DelayCategories | Governance
DelayCategories | Exogenous
DelaySubcategories | Public_Comment
DelaySubcategories | Required_Wait_Period
DelaySubcategories | Consultation_ESA
DelaySubcategories | Consultation_NHPA
DelaySubcategories | Incomplete_Submittal
DelaySubcategories | Alt_Analysis_Rework
DelaySubcategories | Modeling_Rework
DelaySubcategories | Design_Change
DelaySubcategories | LeadCoop_Misalignment
DelaySubcategories | Staff_Turnover
DelaySubcategories | Sequencing_NEPA_404
DelaySubcategories | Tribal_Consultation_Cadence
DelaySubcategories | Litigation
DelaySubcategories | Policy_Change
DelaySubcategories | Land_Ownership_Change
DelaySubcategories | EIS_Denial
Owners | Sponsor
Owners | Lead_Agency
Owners | Cooperating_Agency
Owners | Court
Owners | External
ActionLevels | EIS
ActionLevels | SEIS
ActionLevels | EA
ActionLevels | CE
Status | in_process
Status | complete
Status | paused
Status | withdrawn
MineTypes | open-pit
MineTypes | underground
MineTypes | in-situ
MineTypes | hybrid
MineTypes | unknown
TailingsTypes | filtered_dry_stack
TailingsTypes | conventional
TailingsTypes | paste
TailingsTypes | centerline
TailingsTypes | downstream
TailingsTypes | upstream
TailingsTypes | in-pit
TailingsTypes | valley_fill
TailingsTypes | none_na
TailingsTypes | unknown
ActionTypes | new_mine
ActionTypes | expansion
ActionTypes | plan_revision
ActionTypes | tailings_expansion
ActionTypes | facility_addition
ActionTypes | closure_reclamation
ActionTypes | land_exchange
Precision | day
Precision | month
Precision | year
Precision | unknown
States | AZ
States | NM
States | NV
States | UT
States | CO
States | CA
States | ID
States | MT
States | WY
States | OR
States | WA
States | MN
States | AK
Roles | lead
Roles | cooperating
Roles | consulting
Roles | participating
DelaySubcategories | Conformity_Determination

## Agencies
agency_id | name | jurisdiction_level | parent_agency_id | website
USACE | U.S. Army Corps of Engineers | federal |  | https://www.usace.army.mil/
USFS | U.S. Forest Service | federal | USDA | https://www.fs.usda.gov/
BLM | Bureau of Land Management | federal | DOI | https://www.blm.gov/
EPA | U.S. Environmental Protection Agency | federal |  | https://www.epa.gov/
FWS | U.S. Fish and Wildlife Service | federal | DOI | https://www.fws.gov/
AZDEQ | Arizona Department of Environmental Quality | state |  | https://azdeq.gov/
ADWR | Arizona Department of Water Resources | state |  | https://new.azwater.gov/
AZGFD | Arizona Game and Fish Department | state |  | https://www.azgfd.com/
AZSHPO | Arizona State Historic Preservation Office | state |  | https://azstateparks.com/shpo
BIA | Bureau of Indian Affairs | federal | DOI | https://www.bia.gov/bia
MEPA | Minnesota Environmental Protection Agency | state

## Projects
project_id | mine_id | title | action_type | start_year | is_active | notes | source_id_primary | created_at | updated_at
prj_morenci_mine_1994_expansion | morenci_mine | Proposed Exchange of Approximately 3,800 Acres of Public Land Near Morenci, AZ, for Other Private Lands of Similar Value in Southeastern Arizona | expansion | 1994-11-03 | 1
prj_carlota_mine_1992_new_mine | carlota_mine | Carlota Mine - Construction and Operation | new_mine | 1992-02-01 | 0 | Purpose: Construct, operate, and reclaim an open pit copper mine near Miami, AZ.
prj_rosemont_mine_2006_new_mine | rosemont_mine | Rosemont Mine - Construction and Operation | new_mine | 2006-07-01 | 0
prj_ray_mine_2013_tailings_expansion | ray_mine | Ray Mine - Construction and Operation of a New Tailings Storage Facility | tailings_expansion | 2013-03-01 | 1 | Purpose: Tailings facility to receive tailings generated at Ray Mine, an existing open pit copper mine located in Pinal County, AZ
prj_ray_mine_1998_land_exchange | ray_mine | Ray Land Exchange/Plan Amendment | land_exchange | 1998-10-26 | 1
prj_northmet_mine_2005_new_EIS | northmet_mine | NorthMet Mining Project and Land Exchange | new_mine | 2005-06-01 | 0
prj_pebble_mine_2018_new_EIS | pebble_mine | Pebble Project | new_mine | 2018-03-29 | 0
prj_robinson_mine_1994_reinstate | robinson_mine | Robinson Project | new_mine | 1994-04-18 | 1
prj_robinson_mine_1994_expansion | robinson_mine | Robinson Project Expansion | facility_addition | 1994-04-18 | 1
prj_greater_phoenix_mine_2015_expansion | greater_phoenix_mine | Greater Phoenix Project | expansion | 2015-09-29 | 1
prj_copper_flat_mine_2012_new_mine | copper_flat_mine | Copper Flat Project | new_mine | 2012-01-09 | 1
prj_montanore_mine_2005_new_mine | montanore_mine | Montanore Mine | new_mine | 2005-07-14 | 0 | there was an EIS process here, didn't work and then sold to another company who is now in the exploration process
prj_rock_creek_mine_1988_new_mine | rock_creek_mine | Rock Creek Mine | new_mine | 1995-10-06 | 0
prj_bagdad_mine_1994_tailings_expansion | bagdad_mine | Bagadad Mine | tailings_expansion | 1994-06-16 | 1

## NEPA_Actions
nepa_id | project_id | action_level | is_supplemental | parent_nepa_id | lead_agency_id | contractor | alt_count_deis | alt_count_feis | scoping_start | scoping_start_precision | scoping_end | scoping_end_precision | NOA_DEIS_date | NOA_DEIS_precision | DEIS_comment_open | DEIS_comment_open_precision | DEIS_comment_close | DEIS_comment_close_precision | NOA_FEIS_date | NOA_FEIS_precision | FEIS_comment_period_end | FEIS_comment_precision | ROD_date | ROD_precision | status | notes | source_id_primary | created_at | updated_at
NEPA_prj_morenci_mine_1994_expansion_EIS | prj_morenci_mine_1994_expansion | EIS | FALSE |  | BLM |  |  |  | 1994-11-01 | month | 1995-12-01 | month | 1995-12-20 | month | 1995-12-20 | month | 1996-02-20 | month | 1996-09-24 | month | 1996-11-12 | month | 1997-02-07 | month | complete
NEPA_prj_carlota_mine_1992_new_EIS | prj_carlota_mine_1992_new_mine | EIS | FALSE |  | USFS |  |  |  | 1992-02-01 | month | 1994-06-01 | month | 1995-02-01 | month | 1995-02-01 | month | 1995-05-01 | month | 1997-07-01 | month | 1997-07-01 | month | 1997-09-01 | month | complete
NEPA_prj_rosemont_mine_2006_new_EIS | prj_rosemont_mine_2006_new_mine | EIS | FALSE |  | USFS |  |  |  | 2006-07-01 | month | 2008-02-01 | month | 2011-09-01 | month | 2011-10-01 | month | 2012-01-01 | month | 2013-12-01 | month | 2014-02-01 | month | 2017-06-01 | month | withdrawn
NEPA_prj_ray_mine_2013_expansion_EIS | prj_ray_mine_2013_tailings_expansion | EIS | FALSE |  | USACE |  |  |  | 2013-03-01 | month | 2013-08-16 | day | 2016-01-01 | month | 2016-01-29 | day | 2016-04-14 | day | 2018-09-07 | day | 2018-10-09 | day | 2018-12-01 | month | complete
NEPA_prj_ray_mine_1998_land_exchange | prj_ray_mine_1998_land_exchange | EIS | FALSE |  | BLM |  |  |  | 1994-12-19 | month | 1995-02-14 | month | 1998-10-28 | day | 1998-10-28 | day | 1999-01-28 | day | 1999-06-25 | day | 1999-07-25 | day | 2000-04-27 | day | complete
NEPA_prj_northmet_mine_2005_new_EIS | prj_northmet_mine_2005_new_EIS | EIS | FALSE |  | USACE |  |  |  | 2005-01-01 | month | 2005-07-01 | day | 2009-10-27 | day | 2009-10-27 | day | 2010-02-03 | day | 2015-10-19 | day | 2015-12-14 | day | 2017-01-01 | day | paused
NEPA_prj_pebble_mine_2018_new_EIS | prj_pebble_mine_2018_new_EIS | EIS | FALSE |  | USACE |  |  |  | 2018-03-29 | day | 2019-02-20 | day | 2019-02-20 | day | 2019-03-01 | day | 2019-07-01 | day | 2020-07-24 | day | 2020-07-24 | month | 2020-11-25 | day | paused
NEPA_prj_robinson_mine_1994_reinstate | prj_robinson_mine_1994_reinstate | EIS | FALSE |  | BLM |  |  |  | 1993-07-02 | day | 1993-08-05 | day | 1994-04-18 | day | 1994-04-18 | day | 1994-06-17 | day | 1994-09-09 | day | 1994-09-09 | day | 1994-09-09 | day | complete
NEPA_prj_robinson_mine_1994_expansion | prj_robinson_mine_1994_reinstate | EIS | FALSE |  | BLM |  |  |  | 2019-04-01 | month | 2020-05-28 | day | 2020-12-04 | day | 2020-12-04 | day | 2021-01-19 | day | 2021-08-06 | day | 2021-09-05 | day | 2021-09-09 | day | complete
NEPA_prj_greater_phoenix_mine_2015_expansion | prj_greater_phoenix_mine_2015_expansion | EIS | FALSE |  | BLM |  |  |  | 2015-10-29 | day | 2017-09-28 | day | 2017-09-28 | day | 2017-09-28 | day | 2017-10-16 | day | 2018-08-03 | day | 2018-09-02 | day | 2018-09-05 | day | complete
NEPA_prj_copper_flat_mine_2012_new_mine | prj_copper_flat_mine_2012_new_mine | EIS | FALSE |  | BLM |  |  |  | 2010-12-01 | month | 2012-01-09 | day | 2015-11-30 | day | 2015-11-30 | day | 2016-01-14 | day | 2019-04-19 | day | 2019-05-19 | day | 2019-08-22 | day | complete
NEPA_prj_montanore_mine_2005_new_mine | prj_montanore_mine_2005_new_mine | EIS | FALSE |  | USFS |  |  |  | 2005-07-14 | day | 2005-09-15 | day | 2009-02-27 | day | 2009-02-27 | day | 2009-04-13 | day | 2015-12-18 | day | 2016-01-19 | day | 2016-02-02 | day | in_process
NEPA_prj_montanore_mine_2022_new_exploration | prj_montanore_mine_2005_new_mine | EA | FALSE |  | USFS |  |  |  | 2022-09-07 | day | 2024-12-01 | month | 2025-01-21 | day | 2025-01-21 | day | 2025-02-20 | day | 2025-06-23 | day | 2025-08-07 | day | 2025-10-06 | day | complete
NEPA_prj_rock_creek_mine_1988_new_mine | prj_rock_creek_mine_1988_new_mine | EIS | FALSE |  | USFS |  |  |  | 1988-01-12 | day | 1993-06-28 | day | 1995-10-06 | day | 1995-10-06 | day | 1995-12-05 | day | 2001-09-21 | day | 2001-10-15 | day | 2003-06-27 | day | withdrawn
NEPA_prj_rock_creek_mine_1988_new_mine | prj_rock_creek_mine_1988_new_mine | EIS | TRUE |  | USFS |  |  |  | 2011-09-13 | day | 2011-09-13 | day | 2016-02-09 | day | 2016-02-09 | day | 2016-04-04 | day | 2018-06-20 | day | 2018-08-23 | day | 2018-08-27 | day | withdrawn | ROD was remanded
NEPA_prj_bagdad_mine_1994_tailings_expansion | prj_bagdad_mine_1994_tailings_expansion | EIS | FALSE |  | USACE |  |  |  | 1994-06-16 | day | 1994-08-13 | day | 1995-08-14 | day | 1995-08-14 | day | 1995-10-17 | day | 1996-02-02 | day | 1996-03-04 | day | 1996-03-06 | day | complete

## Delays
delay_id | project_id | nepa_id | phase_id | category | subcategory | owner | start_date | start_precision | end_date | end_precision | relevant_legislation | why | notes | source_id_primary
DELAY_prj_carlota_mine_1992_new_mine_consult_esa_95_96 | prj_carlota_mine_1992_new_mine | NEPA_prj_carlota_mine_1992_new_EIS |  | Process | Incomplete_Submittal | Sponsor | 1992-02-01 | month | 1994-06-01 | month |  | Carlota mine initially submitted MPO in 1992, but after scoping conversations and additional work was done, and in response to agency + public comments, they submitted an updated plan in 1993, and a closure and reclamation plan in june 1994.
DELAY_prj_carlota_mine_1992_new_mine_scoping_delay | prj_carlota_mine_1992_new_mine | NEPA_prj_carlota_mine_1992_new_EIS |  | Process | Consultation_ESA | Lead_Agency | 1995-06-19 | day | 1996-04-24 | day | Endangered Species Act Consultation | ESA consultation paused to include hedgehog/cactus in BO; additional data collection.
DELAY_prj_carlota_mine_1992_new_mine_conformity_96_97 | prj_carlota_mine_1992_new_mine | NEPA_prj_carlota_mine_1992_new_EIS |  | Process | Policy_Change | Lead_Agency | 1996-01-01 | day | 1997-06-30 | day | Clean Air Act Conformity Determination | EPA General Conformity determination required prior to decision, 1996–1997.
DELAY_prj_carlota_mine_1992_new_mine_EAB_review | prj_carlota_mine_1992_new_mine | NEPA_prj_carlota_mine_1992_new_EIS |  | Exogenous | Litigation | Court | 2000-08-24 | day | 2004-09-30 | day | NPDES | EAB review of NPDES (initial & reissued) before final effectiveness.
DELAY_prj_carlota_mine_1992_new_mine_9th_vacated | prj_carlota_mine_1992_new_mine | NEPA_prj_carlota_mine_1992_new_EIS |  | Exogenous | Litigation | Court | 2007-10-04 | day | 2008-01-01 | day | NPDES | 9th Cir. vacated EPA NPDES; project pivoted to operate without NPDES.
DELAY_prj_rosemont_mine_2006_new_mine_ESA_ROD | prj_rosemont_mine_2006_new_mine | NEPA_prj_rosemont_mine_2006_new_EIS |  | Process | Consultation_ESA | Lead_Agency | 2014-05-14 | day | 2016-04-28 | day | Endangered Species Act Consultation
DELAY_prj_rosemont_mine_2006_new_mine_NEPA_lit | prj_rosemont_mine_2006_new_mine | NEPA_prj_rosemont_mine_2006_new_EIS |  | Exogenous | Litigation | Court | 2017-09-25 | day | 2022-05-12 | day | Endangered Species Act Consultation | NEPA approvals challenged; FEIS/ROD vacated and affirmed on appeal.
DELAY_prj_rosemont_mine_2006_new_mine_404_lit | prj_rosemont_mine_2006_new_mine | NEPA_prj_rosemont_mine_2006_new_EIS |  | Exogenous | Litigation | Court | 2019-03-27 | day | 2023-03-30 | day | Section 404 | 404 permit challenged; later surrendered and revoked.
DELAY_prj_northmet_mine_2005_new_mine_FLPMA_lit | prj_northmet_mine_2005_new_EIS | NEPA_prj_northmet_mine_2005_new_EIS |  | Exogenous | Litigation | Court | 2017-01-30 | day | 2019-09-30 | day | Federal Land Policy and Management Act | this and the next three legal cases were consolidated
DELAY_prj_northmet_mine_2005_new_mine_NEPA_lit | prj_northmet_mine_2005_new_EIS | NEPA_prj_northmet_mine_2005_new_EIS |  | Exogenous | Litigation | Court | 2017-01-30 | month | 2019-09-30 | day | NEPA
DELAY_prj_northmet_mine_2005_new_mine_ESA_lit | prj_northmet_mine_2005_new_EIS | NEPA_prj_northmet_mine_2005_new_EIS |  | Exogenous | Litigation | Court | 2017-01-30 | month | 2019-09-30 | day | Endangered Species Act Consultation
DELAY_prj_northmet_mine_2005_new_mine_FLPMA_lit | prj_northmet_mine_2005_new_EIS | NEPA_prj_northmet_mine_2005_new_EIS |  | Exogenous | Litigation | Court | 2017-01-30 | month | 2019-09-30 | day | Federal Land Policy and Management Act
DELAY_prj_northmet_mine_2005_new_mine_NPDES_lit | prj_northmet_mine_2005_new_EIS | NEPA_prj_northmet_mine_2005_new_EIS |  | Exogenous | Litigation | Court | 2019-01-22 | day | 2023-08-02 | day | NPDES
DELAY_prj_northmet_mine_2005_new_mine_404_lit | prj_northmet_mine_2005_new_EIS | NEPA_prj_northmet_mine_2005_new_EIS |  | Exogenous | Litigation | Court | 2020-06-29 | day | 2021-03-04 | day | Section 404
DELAY_prj_northmet_mine_2005_new_mine_air_emissions_lit | prj_northmet_mine_2005_new_EIS | NEPA_prj_northmet_mine_2005_new_EIS |  | Process | Incomplete_Submittal | Court | 2020-03-20 | day | 2023-12-18 | day | Air Emissions Permit
DELAY_prj_pebble_mine_2018_new_404_rejection | prj_pebble_mine_2018_new_EIS | NEPA_prj_pebble_mine_2018_new_EIS |  | Process | EIS_Denial | Lead_Agency | 2021-01-01 | month | 2024-04-15 | day
DELAY_prj_pebble_mine_2018_new_404_rejection | prj_pebble_mine_2018_new_EIS | NEPA_prj_pebble_mine_2018_new_EIS |  | Exogenous | Litigation | Court | 2019-10-08 | day | 2020-04-17 | day | Section 404 |  | After the EPA decided to withdraw its decision to deny Pebble's 404 clean water act permit, environmental groups sued and court determined that the proposal to withdraw needed to be re-done. In 2023, the EPA issued a final determination denying the permit. State of Alaska tried and failed to undo it.
DELAY_prj_pebble_mine_2018_new_404_appeal | prj_pebble_mine_2018_new_EIS | NEPA_prj_pebble_mine_2018_new_EIS |  | Exogenous | Litigation | Court | 2023-07-26 | day | 2024-01-08 | day | Section 404 |  | This is the state of alaska suing the EPA by saying they should continue to withdraw their proposal to stay 404 determinations.
DELAY_prj_pebble_mine_2018_new_ROD_appeal_lit | prj_pebble_mine_2018_new_EIS | NEPA_prj_pebble_mine_2018_new_EIS |  | Exogenous | Litigation | Court | 2024-04-15 | day | 2025-10-03 | day | Section 404 |  | This is pebble mine's ongoing litigation suing the USACE to issue a section 404 permit. Three cases were consolidated here.
DELAY_prj_copper_flat_mine_2012_new_public_comment_delay | prj_copper_flat_mine_2012_new_mine | NEPA_prj_copper_flat_mine_2012_new_mine |  | Process | Public_Comment | Lead_Agency | 2016-02-02 | day | 2016-04-04 | day
DELAY_prj_copper_flat_mine_2012_new_water_rights_lit | prj_copper_flat_mine_2012_new_mine | NEPA_prj_copper_flat_mine_2012_new_mine |  | Exogenous | Litigation | Court | 2018-02-28 | day | 2023-12-12 | day | Water Rights | Lawsuit regarding the water rights available to the operator (NMCC).
DELAY_prj_copper_flat_mine_2012_new_water_right_transfer | prj_copper_flat_mine_2012_new_mine | NEPA_prj_copper_flat_mine_2012_new_mine |  | Exogenous | Litigation | Court | 2019-08-01 | month | 2025-09-05 | day | Water Rights | New Mexico State Engineer denied water rights transfer to NMCC to use different water source for Copper Flat mine.
DELAY_prj_copper_flat_mine_2012_new_rescind_technical_approvability | prj_copper_flat_mine_2012_new_mine | NEPA_prj_copper_flat_mine_2012_new_mine |  | Process | Incomplete_Submittal | Cooperating_Agency | 2020-03-31 | day | 2020-06-05 | day | State Permit | NMCC wasn't able to get water rights for a bunch of years, thus the New Mexico Energy, Minerals, and Natural resources board rescinded the notice of technical approvability. They then doubled back and withdrew there approvals, but the issues remain. Water rights still need to be shown. | This was the Notice of Technical Approvability
DELAY_prj_montanore_mine_2005_new_mine_ROD_lit | prj_montanore_mine_2005_new_mine | NEPA_prj_montanore_mine_2005_new_mine |  | Exogenous | Litigation | Court | 2016-04-05 | day | 2017-06-17 | day | Administrative Procedure Act | ROD was denied and pushed back
DELAY_prj_montanore_mine_2005_new_mine_SEIS | prj_montanore_mine_2005_new_mine | NEPA_prj_montanore_mine_2005_new_mine |  | Process | Modeling_Rework | Lead_Agency | 2017-12-28 | day | 2019-08-08 | day
DELAY_prj_montanore_mine_2005_new_mine_SEIS | prj_montanore_mine_2005_new_mine | NEPA_prj_montanore_mine_2005_new_mine |  | Process | Incomplete_Submittal | Sponsor | 2019-08-08 | day | 2022-06-17 | day |  |  | Sponsor withdrew their proposal of operations which led the USFS to withdraw their draft eis proposal.
DELAY_prj_rock_creek_mine_1995_new_mine_public_comment_period | prj_rock_creek_mine_1988_new_mine | NEPA_prj_rock_creek_mine_1988_new_mine |  | Process | Public_Comment | External | 1995-11-14 | day | 1996-04-22 | day | State Permit | Lots of comments about MPDES (minnesota) permit and water quality
DELAY_prj_rock_creek_mine_1995_new_mine_SEIS | prj_rock_creek_mine_1988_new_mine | NEPA_prj_rock_creek_mine_1988_new_mine |  | Process | Modeling_Rework | Lead_Agency | 1996-04-22 | day | 1998-01-09 | day |  | SEIS needed to respond to comments
DELAY_prj_rock_creek_mine_1995_new_mine_incomplete_MPO | prj_rock_creek_mine_1988_new_mine | NEPA_prj_rock_creek_mine_1988_new_mine |  | Process | Incomplete_Submittal | Sponsor | 1988-01-27 | day | 1993-05-27 | day |  | ASARCO had to rework their MPO, in specific their waste water plan
DELAY_prj_rock_creek_mine_1995_new_mine_ESA_lit | prj_rock_creek_mine_1988_new_mine | NEPA_prj_rock_creek_mine_1988_new_mine |  | Process | Litigation | Court | 2001-08-28 | day | 2010-05-04 | day | Endangered Species Act | Litigating the USFWS biological opinion, saying it would harm grizzlies and trout. | Went back and forth, USFWS issued two biological opinions between 2001 and 2005 and the court agreed that the final USFWS biological opinion was not adequate. I'm grouping in all of the lawsuits here that led up to the repeal of the 2003 ROD
DELAY_prj_rock_creek_mine_1995_new_mine_MPDES_lit | prj_rock_creek_mine_1988_new_mine | NEPA_prj_rock_creek_mine_1988_new_mine |  | Process | Litigation | Court | 2002-01-28 | day | 2008-12-04 | day | State Permit | Environmental groups argue that Minnesota illegally issued a MPDES permit
DELAY_prj_rock_creek_mine_1995_new_mine_MPDES_lit | prj_rock_creek_mine_1988_new_mine | NEPA_prj_rock_creek_mine_1988_new_mine |  | Process | Litigation | Court | 2019-01-25 | day | 2021-04-14 | day | Endangered Species Act | Environmental groups again target the endangered species act, and a federal court vacated the 2008 ROD for the supplemental EIS.
DELAY_prj_ray_mine_1998_land_exchange_EIS_lit | prj_ray_mine_1998_land_exchange | NEPA_prj_ray_mine_1998_land_exchange |  | Process | Litigation | Court | 2001-07-01 | month | 2010-11-19 | day |  | litigation against the ROD of the land exchange saying adequate analysis was not done
DELAY_prj_ray_mine_1998_land_exchange_SEIS_dev | prj_ray_mine_1998_land_exchange | NEPA_prj_ray_mine_1998_land_exchange |  | Process | EIS_Denial | Court | 2010-11-19 | month | 2019-07-01 | day |  | SEIS preparation
DELAY SEIS for Montanore?
Set SEIS as delay?

## NEPA_Action_Agencies
nepa_agency_id | nepa_id | agency_id | role | start_date | end_date | notes | source_id_primary
NEPAG_carlota_usfs | NEPA_prj_carlota_mine_1992_new_EIS | USFS | lead |  |  | Tonto National Forest
NEPAG_carlota_azdeq | NEPA_prj_carlota_mine_1992_new_EIS | AZDEQ | cooperating |  |  | State water quality cooperator
NEPAG_carlota_usace | NEPA_prj_carlota_mine_1992_new_EIS | USACE | cooperating |  |  | Corps involvement (jurisdictional waters)
NEPAG_rosemont_usfs | NEPA_prj_rosemont_mine_2006_new_EIS | USFS | lead
NEPAG_rosemont_blm | NEPA_prj_rosemont_mine_2006_new_EIS | BLM | cooperating
NEPAG_rosemont_azde | NEPA_prj_rosemont_mine_2006_new_EIS | AZDEQ | cooperating
NEPAG_ray_usace | NEPA_prj_ray_mine_2013_expansion_EIS | USACE | lead
NEPAG_ray_usace | NEPA_prj_ray_mine_2013_expansion_EIS | BLM | cooperating
NEPAG_ray_usace | NEPA_prj_ray_mine_2013_expansion_EIS | BIA | cooperating |  |  | San Carlos Irrigation Project (SCIP)
NEPAG_ray_usace | NEPA_prj_ray_mine_2013_expansion_EIS | EPA | cooperating

## Permits
permit_id | project_id | permit_type | permit_subtype | agency_id | application_date | complete_date | decision_date | decision | notes | source_id_primary | created_at | updated_at

## Legal_Cases
case_id | project_id | court_level | court_name | case_name | docket_number | filing_date | injunction_issued | injunction_start | injunction_end | relevant_permit | relevant_EIS | decision_date | disposition | claims | notes | docket_url | source_id_primary
case_prj_carlota_1992_new_mine_EAB_2000 | prj_carlota_mine_1992_new_mine | Administrative | EPA Environmental Appeals Board | IN RE CARLOTA COPPER COMPANY: ORDER DENYING REVIEW |  | 2000-08-25 | FALSE |  |  | NPDES | FEIS | 2002-02-27 | Petition Denied |  | The inital petition caused the region to request a stay to address issues.
case_prj_carlota_1992_new_mine_EAB_2002 | prj_carlota_mine_1992_new_mine | Administrative | EPA Environmental Appeals Board | IN RE CARLOTA COPPER COMPANY: ORDER DENYING REVIEW |  | 2002-04-01 | FALSE |  |  | NPDES | FEIS | 2004-09-30 | Finding of No Significant Impact
case_prj_carlota_1992_new_mine_9th_2007 | prj_carlota_mine_1992_new_mine | Federal Circuit | U.S. Court of Appeals for the Ninth Circuit | Friends of Pinto Creek v. EPA | 05-70785 | 2006-11-13 | TRUE |  |  | NPDES | FEIS | 2007-10-01 | NPDES Vacated
case_prj_rosemont_mine_2006_new_mine_DAZ_2019 | prj_rosemont_mine_2006_new_mine | Federal District | U.S. District Court, District of Arizona | Center for Biological Diversity et al. v. U.S. Fish & Wildlife Service et al. (consolidated) | 4:17-cv-00475-JAS | 2017-09-25 | TRUE |  |  |  | FEIS | 2019-07-31 | FEIS and ROD vacated and remanded
case_prj_rosemont_mine_2006_new_mine_9th_2022 | prj_rosemont_mine_2006_new_mine | Federal Circuit | U.S. Court of Appeals for the Ninth Circuit | Center for Biological Diversity v. U.S. Fish & Wildlife Service | 19-17585 | 2021-02-01 | TRUE |  |  |  | FEIS | 2022-05-12 | Affirmed district court vacatur of FEIS/ROD
case_prj_rosemont_mine_2006_new_mine_DAZ_2019 | prj_rosemont_mine_2006_new_mine | Federal District | U.S. District Court, District of Arizona | Save the Scenic Santa Ritas et al. v. U.S. Army Corps of Engineers |  | 2019-03-27 | TRUE |  |  | 404 | FEIS | 2023-03-30 | Case became moot, rosemont surrendered. Permit eventually revoked.

## Case_Links
case_link_id | case_id | target_type | target_id | relation | notes

## Events
event_id | project_id | nepa_id | permit_id | case_id | event_type | event_date | date_precision | description | source_id_primary

## Phases
phase_id | nepa_id | phase_type | start_date | start_precision | end_date | end_precision | notes | source_id_primary

## Comments_Summary
nepa_id | period | comment_count | topic_water | topic_tailings | topic_cultural | topic_air | topic_traffic | topic_GHG | summary_link | source_id_primary

## Documents
document_id | project_id | nepa_id | permit_id | doc_type | title | agency_id | published_date | url | notes | source_id_primary

## Sources
source_id | citation | title | url | access_date | notes
ray_mine_feis
ray_mine_tailings_feis_exec_summary |  | RAY MINE TAILINGS STORAGE FACILITY EIS EXECUTIVE SUMMARY | https://www.spl.usace.army.mil/Portals/17/docs/regulatory/Projects/Ray_Mine/Final_EIS/Executive-Summary.pdf?ver=2018-09-06-134858-410 | 2025-09-30
ray_mine_land_exchange_noa_rod_feis_supplemental |  | Notice of Availability of Record of Decision for the Ray Land Exchange Final Supplemental Environmental Impact Statement/Proposed Plan Amendment, Arizona | https://www.federalregister.gov/documents/2019/11/04/2019-24056/notice-of-availability-of-record-of-decision-for-the-ray-land-exchange-final-supplemental | 2025-09-30
ray_mine_land_exchange_noa_rod_eis_supplemental |  | Ray Land Exchange/Plan Amendment (Supplemental) | https://eplanning.blm.gov/eplanning-ui/project/82268/510 | 2025-09-30
ray_mine_tailings_draft_eis |  | DRAFT ENVIRONMENTAL IMPACT STATEMENT Proposed Mine Tailings Storage Facility Ray Mine — Pinal County, Arizona | https://www.resolutionmineeis.us/sites/default/files/references/usace-2016.pdf | 2025-09-30
ray_mine_tailings_feis_ch1-9 |  | RAY MINE TAILINGS STORAGE FACILITY FACT SHEET AND FINAL EIS CHAPTERS 1-9 | https://minedocs.com/22/Ray-EIS-August2018.pdf | 2025-09-30
ray_mine_tailings_noa_draft_eis |  | NOTICE OF AVAILABILITY OF DRAFT EIS AND ANNOUNCEMENT OF A PUBLIC MEETING Ray Mine Proposed Tailings Storage Facility | https://www.spl.usace.army.mil/Portals/17/docs/publicnotices/SPL-2011-01005-MWL%20EIS%20PN.pdf?ver=vaTJH1DcUm9_oxc43vAz6A%3d%3d | 2025-09-30
ray_mine_tailings_rod |  | RECORD OF DECISION Ray Mine Tailings Storage Facility | https://www.spl.usace.army.mil/Portals/17/docs/regulatory/Projects/Ray_Mine/SPL-2011-01005-MWL%20Ray%20Mine%20Tailings%20Storage%20Facility.pdf?ver=2018-12-14-163405-273 | 2025-09-30 | summary of comments here

## Resource Guide
Ray Mine Documents USACE Index | https://www.spl.usace.army.mil/Missions/Regulatory/Projects-Programs/
Ray Mine Draft Documents USACE Index | https://www.spl.usace.army.mil/Missions/Regulatory/Projects-Programs/Ray-Mine-Tailings-Storage-Facility/

## ID Definitions
| ID | Definition | Comment
Mines
| mine_id | Primary reference ID for each profiled mine
| name | Name of mine
| operator | Lead mine operator/owner (majority stake) | Do we want to include companies that hold a minor stake in the mine?
| commodity_primary | Main mineral being extracted from mine
| commodity_secondary | Secondary mineral(s) being extracted from mine
state
county
lat
lon
land_status_mix
mine_type
tailings_type
description
notes
source_id_primary
created_at
updated_at
Projects
project_id
mine_id
title
action_type
start_year
| is_active | Is the mine currently producing/active?
notes
source_id_primary
created_at
updated_at
agencies
agency_id
name
jurisdiction_level
parent_agency_id
website
NEPA_Actions
nepa_id
project_id
action_level
| is_supplemental | Is the EIS a supplemental
parent_nepa_id
lead_agency_id
contractor
alt_count_deis
alt_count_feis
| scoping_start | Date of first action for mine/project development
scoping_start_precision
scoping_end
scoping_end_precision
NOA_DEIS_date
NOA_DEIS_precision
DEIS_comment_open
DEIS_comment_open_precision
DEIS_comment_close
DEIS_comment_close_precision
NOA_FEIS_date
NOA_FEIS_precision
FEIS_comment_period_end
FEIS_comment_precision
ROD_date
ROD_precision
status
notes
source_id_primary
created_at
updated_at
NEPA_Actions_Agencies
nepa_agency_id
nepa_id
agency_id
role
start_date
end_date
notes
source_id_primary
Permits
permit_id
project_id
permit_type
permit_subtype
agency_id
application_date
complete_date
decision_date
decision
notes
source_id_primary
created_at
updated_at
Legal_Cases
case_id
project_id
court_level
court_name
case_name
docket_number
filing_date
injunction_issued
injunction_start
injunction_end
relevant_permit
relevant_EIS
decision_date
disposition
claims
notes
docket_url
source_id_primary
Case_Links
case_link_id
case_id
target_type
target_id
relation
notes
Events
event_id
project_id
nepa_id
permit_id
case_id
event_type
event_date
date_precision
description
source_id_primary
Phases
phase_id
nepa_id
phase_type
start_date
start_precision
end_date
end_precision
notes
source_id_primary
Delays
delay_id
project_id
nepa_id
phase_id
category
subcategory
owner
start_date
start_precision
end_date
end_precision
relevant_legislation
why
notes
source_id_primary
Comments_Summary
nepa_id
period
comment_count
topic_water
topic_tailings
topic_cultural
topic_air
topic_traffic
topic_GHG
summary_link
source_id_primary
Documents
document_id
project_id
nepa_id
permit_id
doc_type
title
agency_id
published_date
url
notes
| source_id_primary |  | should it be source_id_primary below?
Sources
source_id
citation
title
url
access_date
notes